## Лист1
main tecnologies: - Java version: 11+ - Maven version: 3.8.* - Spring Boot version: 2.7.*.RELEASE - GitHub - H2 in-memory database - JPA - Postman
Idea: creating a backend for Pizza project with Rest API
Before start: Think about security, for example only admin can add, delete and update data.
week#1
task#1 Describe the work of the pizza project in detail
Use: Word, Notepad or any
As min result, it must be reflected: description project, Repository layer, Service layer, Entity
task#2 Create ERD database schema.
Use: MySQL Workbench, Violet UML Editor or any
As min result, it must be reflected: database diagram with relationships
task#3 Describe REST Open API
Use: Word office, AsciiDoc or any
As min result, it must be reflected: Document with a description of the endpoints
task#4 Create a repository and project for work
note:1) repository and project can be created in a personal account or in Telran githab, 2) can be private: add the curator to the project
main: to add repository name <last name>-java-pizzaproject, to add project name <last name>-JAVA-PIZZAPROJECT, to add project description, choose Project template: kanban
As min result, it must be reflected: repository in GitHub, a project ready for cloning, the tasks entered in the planner of GitHub (you can see the tasks below)
week #2
[FEATURE] JAVAPP-1: create Spring boot project
description: create a Spring Boot project, add all required dependencies
As min result, it must be reflected: working project
[FEATURE] JAVAPP-2: Add repository layer
description: Add a repository layer to the project.
As min result, it must be reflected: Create a repository package, an entity package, all the necessary entities, an interface for working with the database and its implementation. Create class InitDataBase and add some pizzas and cafes programmatically.
week #3
[FEATURE] JAVAPP-3: Add H2
description: add H2 in-memory database and configure it in the application.properties file
As min result, it must be reflected: Add dependency to Pom
[FEATURE] JAVAPP-4: Add controllers
description: Create the controllers for the Pizza and Cafe models and test the basic CRUD operations using Postman.
As min result, it must be reflected:Test the API using Postman and make sure that all endpoints are working as expected.
This includes sending requests to the API and checking the response to make sure that the API is working correctly.
week #4
[FEATURE] JAVAPP-5: Add validation to your project
description: Create validation for the models using Hibernate Validator
As min result, it must be reflected: Add validation for request parameters using @Valid annotation
[FEATURE] JAVAPP-6: Add Spring Security for authentication and authorization.
description: Add Spring Security for authentication and authorization.
As min result, it must be reflected: POST, DELETE, PUT request is secured with username admin and password admin and CSRF disabled just for testing purpose
week#5
[FEATURE] JAVAPP-7:JUnit tests
description: Covering services with functional tests
As min result, it must be reflected: Unit tests for service and controllers classes
[FEATURE] JAVAPP-8: Heroku (optional)
description: deploy the app to remote server
As min result, it must be reflected: Create a Heroku account and install the Heroku CLI. Create a new app on Heroku and configure the necessary settings, such as the buildpack and runtime environment. Push the application to the Heroku app using Git. Test the deployed application to make sure it is working as expected. Configure the necessary add-ons and environment variables for the deployed application.